Cyclone PAM: Food Security and Agriculture Cluster

Daily Briefing

Date 17 March 2015

1:00pm

Food Security and Agriculture Cluster 
Lead Organisations: DARD, SPC/GIZ, FAO

Urgent Needs:

- Quantify all stocks of imported and local foods on all islands (Vila and Luganville stocks are already well known) - Identify the sources and types of vegetative panting material ressources avilable on all islands (especially stocks of kumala vine cuttings and island cabbage branches) - Urgent commitment from Government Finance and International Agencies for quickly available finance to purchase locally available supplies (see budget below) - Development of guidelines for food distribution on islands, based on local context - A large cadre of local volunteers to assemble food aid packages for island delivery - Commitment from VMF and Policy staff to travel with to supervise food aid delivery to islands - Support for air drops flyers of key messages to farmers to immediately replant - Satellite phone communication with island-based food security officers and key farmers.

Response (high priority actions)

- Comunication of key food security messages (FM & HF radio, pamphlet, mobile, newspaper) has begun - Preparation of a national estimate of type and quantity of food required for each island, based on damage and population - Agriculture experts are analysing the areal picture to determine damage on crops, fruits, livestock and fisheries infrastructure - The preparation of a standard food package, including critical calories, has been finslized - Agriculture and Food Security Rapid Assessment Teams already flying to Tanna and Erromango - Stocktake of all avialble food stuffs, seeds and farming tools has been completed for Port Vila and Luganville - A stocktake of all available high quality planting materials is being undertaken - Island level maps of food distribution plans are being prepared

Gaps & Constraints (beneficiary needs)

Finance: - ~ 400, 000 Vt per day per ship (example: ~ 5.6 million Shipping 2 weeks to Shepherds Island alone) - ~ 3.3 Million Vt pest and disease assessment budget - ~ 11 Million Vt for vegetable seeds for 3 months for all islands - ~ 1 million Land Transport from - ~ 160 million Purchase of Locally Available Food Supplies (rice/biscuits/tins) HR: - Local Volunteers for assemblyng the food for the food packages - International Expertise on lare scale food distribution logistics and processes - Overseas secretariat support to type handwritten plans and update online coordination websites/google docs