Cyclone PAM: Food Security and Agriculture Cluster

Daily Briefing

Date 30 March 2015

1:00pm

Food Security and Agriculture Cluster 
Lead Organisations: DARD, SPC/GIZ, FAO

Urgent Needs:

- Long term rebuilding and restructuring of the Ministry (MLFFB) - Fishing gear (boats, nets etc) - Food rations for boarding schools - Animal welfare support (animal feed, water, shelter)

Response (high priority actions)

- International procurement of non-perishable emergency food stocks complete for next push of food WFP: 200MT rice, German Government: 137MT rice, Red Cross: 108MT, Adra: 25MT rice. Further procurement is underway for the for the longer term food assistance response. - First Push Food Distribution fully complete: SHEFA: Shepherds islands, Efate Offshore (3,088 people), Epi (7,621 people) TAFEA (Aneityum, Aniwa), MALAMPA (Paama) - Food distribution close to completion: EFATE: Port Vila urban and peri-urban (18,512 households) - Food Distribution underway: PENAMA (Pentecost, Maewo; 4,800 households), TORBA (Mere Lava; 100 households), MALAMPA (Ambrym, 1,500 households), TAFEA (Tanna, Erromango; 5,900 households) - Dispatch and Distribution of High Energy Biscuits (HEB) to approximately 38,000 people in 9 priority islands with water shortages in Shefa and Tafea province; including dispatch of 31MT of HEB in Tanna - Assessment of fisheries damage and of fish preservation and fishing facilities on Shepherd Islands and Efate offshore islands completed: 90-95% of fishing gears have been destroyed - Evaluation of availability of surplus fresh produce from less impacted islands has been undertaken including Fiji taro, island taro, cassava, kumula, yams, as well as for fishing by-catch. Transport and logistics options for these are being investigated. - Assessments on plant diseases and animal welfare on Epi is completed, need of water shelter and food - Development of long term recovery plan (forestry, fishery, agriculture)

Gaps & Constraints (beneficiary needs)

- Reliable statistics on number of households at the Area Council and village level - Assessments for second food distribution and mid-term and long-term planning - Transport of food and seeds from inter island and on the island - Information on number of people received food packages is not clearly being reported in a systematic way - Volunteers needed: seed re-packaging, trained food distribution observers